## Dashboard
|  | Sprint | 5
Row Labels | Sum of Commits | Row Labels | Sum of Commits
1 | 33 | Andrew | 7
2 | 38 | Ava | 4
3 | 31 | Carlos | 8
4 | 39 | Payton | 10
5 | 38 | Rachel | 9
Grand Total | 179 | Grand Total | 38

## Progress
Metric | Hours | Tasks
Actual | 744 | 306
Budget Project to Date | 750 | 294
Total | 2250 | 814
Status | 0.8% | 4.082%
Color | Green | Green

## Commits
Sprint | Developer | Commits
1 | Rachel | 7
1 | Andrew | 5
1 | Payton | 7
1 | Carlos | 9
1 | Ava | 5
2 | Rachel | 4
2 | Andrew | 10
2 | Payton | 4
2 | Carlos | 10
2 | Ava | 10
3 | Rachel | 4
3 | Andrew | 4
3 | Payton | 6
3 | Carlos | 7
3 | Ava | 10
4 | Rachel | 10
4 | Andrew | 7
4 | Payton | 7
4 | Carlos | 9
4 | Ava | 6
5 | Rachel | 9
5 | Andrew | 7
5 | Payton | 10
5 | Carlos | 8
5 | Ava | 4
6
6
6
6
6
7
7
7
7
7
8
8
8
8
8
9
9
9
9
9
10
10
10
10
10
11
11
11
11
11
12
12
12
12
12
13
13
13
13
13
14
14
14
14
14
15
15
15
15
15

## Phases
Feature | Start | End | Blank | Complete | Future
Database | 1 | 2 | End | 2 | 0
User Login | 3 | 3 | 2 | 1 | 0
User Maintenance | 4 | 6 | 3 | 2 | 1
Time Entry | 7 | 9 | 6 | 0 | 3
Time Edit | 10 | 12 | 9 | 0 | 3
Review | 13 | 13 | 12 | 0 | 1
Submit | 14 | 15 | 13 | 0 | 2

## Layout
Hours to budget bullet
Tasks to budget bullet
code commitments by sprint line
code commitments by developer this sprint column
Gantt showing completeness
Overall status